## firstDraft
Day | Phase | Goal | Subham (AI/ML) | Subir (Fullstack) | Hemant (GCP/Integration) | Intern (Support)
1–2 | Planning & Setup | Finalize architecture, set up infra & repos | Define AI pipeline, research ontologies | Set up frontend boilerplate, wireframes | Provision GCP services, IAM roles | Create docs, gather sample specs
3–4 | Input Parsing & Understanding | Build ingestion pipeline, parse requirements | Gemini prompt tuning, domain classifier | Upload interface for PDF/Word/XML | Connect ALM APIs, store parsed data in BigQuery | Validate outputs, assist with test data
5–6 | Test Case Generation | Generate test cases, map to compliance | Build generation logic, embed compliance rules | Display test cases in UI | Store cases in Firebase, enable sync | Review cases, assist feedback loop
7 | Traceability & Audit | Build traceability matrix, enable audit logs | Link REQ ↔ TC ↔ Defects, traceability logic | Matrix UI with filters/export | Audit logs in Firebase, compliance scoring | Test matrix, simulate audit scenarios
8 | Enterprise Integration | Connect Jira/Azure/Polarion, enable sync | Define sync triggers, regeneration logic | Integration settings UI | API connectors with error handling | Test sync flows, document integration
9 | GDPR PoC Mode & Scalability | Enable data masking, prepare PoC deployment | Implement masking logic, validate GDPR | PoC mode toggle in UI | Deploy microservices, test scalability | Run dummy PoC, collect feedback
10 | Demo Prep & Final Polish | Finalize UI, prepare pitch/demo | Prepare demo script, highlight AI/compliance | Polish UI, add export features | Optimize backend, ensure analytics live | QA testing, prepare docs, assist pitch deck

## FD+genai
Day | Phase | Goal | Subham (AI/ML, GenAI) | Subir (Fullstack) | Hemant (GCP/Integration) | Intern (Support)
1–2 | Planning & Setup | Finalize architecture, set up infra & repos | Define GenAI pipeline, research healthcare ontologies | Set up frontend boilerplate, wireframes | Provision Vertex AI, BigQuery, Firebase | Create docs, gather sample specs
3–4 | Requirement Parsing | Build ingestion pipeline, parse requirements | Gemini prompt tuning, domain classifier | Upload interface for PDF/Word/XML | Connect ALM APIs, store parsed data in BigQuery | Validate outputs, assist with test data
5–6 | Test Case Generation | Generate test cases, map to compliance | Build GenAI test generation logic, embed compliance rules | Display test cases in UI | Store cases in Firebase, enable sync | Review cases, assist feedback loop
7 | Traceability & Audit | Build traceability matrix, enable audit logs | Link REQ ↔ TC ↔ Defects, traceability logic | Matrix UI with filters/export | Audit logs in Firebase, compliance scoring | Test matrix, simulate audit scenarios
8 | Enterprise Integration | Connect Jira/Azure/Polarion, enable sync | Define sync triggers, regeneration logic | Integration settings UI | API connectors with error handling | Test sync flows, document integration
9 | GDPR PoC Mode & Scalability | Enable data masking, prepare PoC deployment | Implement masking logic, validate GDPR | PoC mode toggle in UI | Deploy microservices, test scalability | Run dummy PoC, collect feedback
10 | Demo Prep & Final Polish | Finalize UI, prepare pitch/demo | Prepare demo script, highlight GenAI/compliance | Polish UI, add export features | Optimize backend, ensure analytics live | QA testing, prepare docs, assist pitch deck